## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Jake Warren G00349377 | Final Draft

## Product No 1 or Sprint No 1
|  | Purpose: | To test the functionality of the developed application
LP (Linear Progression) |  |  |  | Visual Studio 2017 VS - Android Emulator Galaxy S10+ (Test Device)
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Main Page | UI | 1. Launch App | Compiling | Main page is displayed | Main page is displayed | Pass
2 | 1 | TC.002 | Display Pages | UI | 1. Launch Application 2. Navigate to different pages | Compiling Navigation | Different pages should display | Different pages are displayed | Pass
3 | 1 | TC.003 | Display Workouts | Functionality | 1. Launch Application 2. Navigate to Main Page 3. Check for stored workouts | Storage | A list of workout should appear | Workouts appear | Pass
4 | 1 | TC.004 | Add Workout | Functionality | 1.Launch Application 2.Navigate to Main Page 3.Scroll down and click Add Workout Button | Navigation | Add workout page should appear | Add Workout page appears | Pass
4 | 1 | TC.005 | Add Workout | Functionality | 1.Launch Application 2.Navigate to Add Workout Page 3.Enter valid details 4.Save | Storage | Workout should be saved and page should be popped back to main page. | Workout is saved and page is popped back. | Pass
4 | 2 | TC.006 | Add Workout | Functionality | 1. Repeat Steps outlined int TC.005 | Storage | Workout should appear in list, it's day (e.g.: 1) being it's title and should increment for each workout present. | Does not increment | Pass | Defect No 1 Priority-2 Severity-Minor | To be fixed. Edit: Has been resolved.
5 | 1 | TC.007 | Navigation | Functionality | 1. Launch Application 2. Navigate to Help Page 3. Click the Squat button | Navigation. | Successful navigation to SquatWiki Page | SquatWiki page is displayed | Pass
5 | 1 | TC.008 | Navigation | Functionality | 1.Repeat steps in TC.007 for the rest of the available buttons on the page | Navigation. | Successful navigation to the relevant Wiki page. | Relevant Wiki page is displayed | Pass
6 | 2 | TC.007.1 | JSON | Database | 1. Restart the application 2.Navigate to main page 3.Check for previously stored workouts. | JSON storage. | Successfully load the list of previously stored workouts. | JSON not functioning, Workouts are not saved to a local database. | Pass | Defect No.2 Priority-1 Severity-Maximum | To be assigned. Edit:Employed SQLLITE. Problem Resolved
7 | 2 | TC.007.2 | JSON | Database | 1. Restart the application 2.Navigate to main page 3.Check for previously stored workouts. | JSON storage. | Successfully load the list of previously stored workouts. | JSON not functioning, Workouts are not saved to a local database. | Pass | Defect No.2 Priority-1 Severity-Maximum | To be assigned. Edit:Employed SQLLITE. Problem Resolved
6 | 2 | TC.008 | UWP | UI | 1. Launch UWP application. 2. Navigate through different pages | UI | Have the UI be consitant between Android and UWP | UI is consistant | Pass
6 | 2 | TC.009.1 | UWP | UI | 1. Launch UWP application. 2. Navigate through different pages | UI | Have the UI be consitant between Android and UWP | UI is consistant | Fail | Defect No.3 Priority-4 Severity - Medium | Navigation bar does not appear on wiki pages. Leading to dead end on UWP
7 | 2 | TC.010 | Charts | Microcharts integration | 1. Launch UWP application. 2. Navigate to the charts page 3. Test chart types | UI | Have a dropdown that lets user choose the exercise they wish to see tracked on a line or bar chart. | Does not function | Fail | Defect No.4 Priority-1 Severity - High | Microcharts latest version causes compile errors. To be resolved
8 | 2 | TC.011 | Deployment | Compile the application into an APK and test on real device. | 1. Compile APK 2.Install APK 3.Repeat Test case Refs: TC.01 -TC.07 | Deployment | App should function similar to the emulator | App functions the same as emulator | Pass

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Test1 | 9 | JW | 1 | All | 5 | 3 | 3 | 55.56%
Test Run description | Test2 | 9 | JW | 1 | N/A | 6 | 2 | 2 | 66.67%
Test Run description | Test3 | 13 | JW | 1 | All | 11 | 2 | 2 | 84.62%
Total |  | 31 |  |  |  | 22 | 7 | 7 | 70.97%